Integrated Seed Sector Development (ISSD) Plus programme in Uganda

Quarterly Reporting – Outscaling Partner (OSP)

CHAIN UGANDA

BUSEGA

AUGUST TO NOVEMBER

APOLLO KASHARU

kasharu@hotmail.com

10TH / December /2017

- Introduction

This quarterly report format should highlight the following: progress with planned activities in the last quarter; challenges and opportunities; lessons learned; plan and budget for the next quarter. Please fill in these requested items under the relevant headings below. Please also fill in the Excel sheet to provide more detailed information on activities carried out by you to support Local Seed Businesses (LSBs) in their efforts to produce quality seed (QDS).

  - Key highlights for the period under review (narrative)

For this reporting period (last quarter), under output 2.2, please describe key activities undertaken, key achievements/progress, key events of interest, including location and target group etc.). The key highlights should include data and be summarized.

CHAIN Uganda, in partnership with ISSD is implementing the local seed business project in the 3 regions of Uganda (South western, Eastern and Rwenzori region).  The rationale and importance of this LSB out scaling program is to sustainably increase the geographic outreach, engage in more crops and varieties as well as involve different types of farmer groups. This is achieved through making a strong joint effort between ISSD Uganda and CHAIN Uganda in which both parties work towards a common goal of sharing and expanding best practices experienced in local seed business to new groups of farmers involved in seed production in Uganda.

The purpose for this report is to highlight the progress so far made on project   implementation.

In the period of August to December 2017, CHAIN Uganda performed several activities in line with project objectives and work plan. The activities were performed aiming at, professionally organizing the farmers to do seed production, technically equipping farmers with skills to produce seed and strategically linking them to organizations that are beneficial to them and orienting them to the markets.

In terms of professionally organization; the groups were trained on organization formation and governance. Consequently, the farmers established organization structures as indicated by formation of committees which are guiding in seed production. Each group has at least 4 major committees namely; executive committee, production committee, quality control committees, marketing committees and finance committees. These committees were trained and skilled to perform their work.

- It is worth mentioning here that the production and quality control committees have been most active as they followed up group members to ensure members adhere to right agronomic practices required for seed production.

- The groups were also trained on resource mobilization and the finance committee was informed that this is their major role to ensure that the group has money Activities.

- The executive committee is also doing its work in some groups as some groups that were just forming are now registered at the town council for example Kibega Farmers group in Mbarara Sanga.

The diagnostic survey was conducted and compiling of the report is being completed for binding.

In terms of technical equipping, some of groups that produce the seeds, a number of activities have been done which include;

- training on pre –planting. Farmers were trained about the land selection, isolation distance, land preparations, row planting and sole planting of the seed, 70% of the farmers have done the right towards these practices however some few farmers are still having problem with line spacing and also planting the seed crop as sole crop as the complain of not having enough land but they want to participate in the seed production.

- Seed delivery and establishment of the seed for demo gardens were also planted. All groups planted demonstration garden which compared performance of farmer’s saved seed and foundation seed. Some groups also included fertilizer trials for purposes of assessing the impact of fertilizers on seed.

- Training in pest and disease management was conducted. Farmers were skilled on pests and diseases identification and as well as how to control them in their gardens.

- Several farm visits to the demonstration gardens were also done at the group level where group members visited their demonstration gardens to assessing the progress and the get the difference of the crops during their growing cycles.

- Field Monitoring by CHAIN staff was also done in all the groups’ gardens to assess the progress.

- Field inspection was also done by both the district inspector and MAAIF.

- Training in post-harvest handling was conducted where farmers were given skills in processing of their seed and proper handling / storage after harvesting.

Towards Market Orientation, the groups were trained on business plans development of their seed production business using Canvass model.

- Group members were taken through sessions of identifying potential markets and how to approach them.

- Some groups have established contacts with government programs (operation wealth creation) and institution seed buyers such as MuZARDI) and Samaritan purse).

Others events that were performed but not planned include,

- CHAIN staff attending the field days that were organized by ISSD in Mbarara and Fortportal.

- CHAIN staff attending the multi-stakeholders meetings in all the regions were also few farmers to of the groups participated

- CHAIN staff attending gender training in all the regions that was organised by ISSD.

- Output 2.2: Additional LSBs developed through partners

Please fill in attached excel table.

- Key results/changes

  - Describe the key results/outcomes of support provided to LSBs

Concrete tangible results/outcomes related to content (skills, capacities, behavior, practices, etc.). Provide a narrative based on analysis of the training evaluation formats.

Farmer groups purchased 3.3 MTs of foundation seed from NaCCRI which established 110 acres of quality declared seed gardens.  Field monitoring indicate about 90% of the gardens will be harvested. The remaining 10% may not perform well especially for the groups that planted on hilly areas where gardens were washed away by running water. This was observed among groups in Ntungamo and also some gardens in eastern region where soil related problems became prominent.

Although it was for the first time for some groups to engage in seed production, farm inspections revealed 93% of the farmers planted seed following the right agronomic practices for seed production. This is contained in the inspectors’ field reports.

To show benefits of seed use and production, 21 demonstration gardens were established by farmers groups. Two groups established for Sweetpotato demos, two groups established demos of soya beans and the rest established beans demo gardens.

Towards skills development the 600 farmers have attained agronomic practices skills required for seed production. This was evident by farmers planting in lines, observing isolation distances, planting seed as sole crop and timely weeding as indicated in monitoring done by the CHAIN staffs and also the inspection reports.

In all the 21 groups 4 committees in each group were trained to perform their roles. Until now, production and quality control committees performed their roles exceedingly well as indicated by training some members on planting in lines, continuous peer field visits, ensuring of roguing off types from gardens and ensuring harvesting at right time. More effort is needed on others committees especially the marketing committee as people have produced the seed but they are not sure of where to sell the beans

  - Intangible results/Outcomes related to process ( collaboration relationships, networking etc.). What other changes have you seen as a result of your engagement with LSB members?

  - Describe what are the key results/outcomes in terms of collaboration with other stakeholders

- Farmers were linked to MAAIF and DAOs for seed and field inspections.

- Some groups have established contacts with government programs (operation wealth creation) and institution seed buyers such as MuZARDI) and Samaritan purse, MBADIFA.

- Farmers  managed to get market for their seed that was produced last season through CHAIN Uganda

- Linkages to Foundation seed suppliers especially NaCRRI

- Lessons learned, challenges and recommendations (in relation to support to LSBs, stakeholder collaboration, engagement with ISSD)

  - Lessons learned

Describe the main lessons learned (what went well, and what did not go well)

- What went well

- Farmers understood more when practical were used in the trainings. Farmers active participation the demos was transferred to their gardens especially line planting.

- The timing of the training also matters. Trainings such as line planting and rogueing, post-harvest processing and handling that coincided with farmer field operations  when the farmers  are going to  apply the practice immediately has made almost all of the farmers to apply the skills received in trainings to produce good seed

- One of the groups which had just formed has been in position to registers at the town council.

- Most of the group’s members have good gardens and will be in position to have good harvests especially those who planted soya and Irish potatoes it has performed extremely well.

- Farmer’s attitude towards trainings has been good and members were able to learn.  This is indicated by high attendance turn up and full engagement in terms asking questions and volunteering responses.

What did not go well?

- Some regions are not good for some seed production, for example, eastern region where this seasons the bean seed was delivered and planted early but still the returns were not good. This implies that the soils and environment in this region does not favor bean production.

- Marketing committee has been formed and trained. Marketing of farmers’ seed is still a challenge in most groups.

  - Challenges faced

- What are some of the challenges you faced?

- Too much rain at the time of planting made some planted gardens to be washed away and harvesting time this has affected the seed color for farmers who had no proper structure for storage.

- Inadequate land for some groups members who have much interest to engage in seed business , these  ended up planting the crop in banana plantations hence making the fields disqualified

- Inadequate equipment’s like tarpaulins and drying racks.

- Too much rain at the time of harvesting has made harvesting of beans hard and affected quality of seed in terms in terms of seed discoloration and rotting.

- Famers groups were expected to pay for the inspection costs for their gardens which have been a challenge to most of the group since farmers were just starting and have not yet known the profitability of business.

- How did you address these challenges if not yet, how do you plan to address these challenges?

- The groups were trained on how to make terraces, contours and plant across to reduce on running water ( erosion)

- The groups in the east next season were advised to try another type of crop for seed for example for the group that planted soya bean their harvests will be good.

- Advised the farmers to do land consolidation or hire a bigger size of land so that they can engage in other seed crops like cassava.

  - Recommendations.

- Proposed recommendations and way forward

- Farmers on hilly arrears to practice soil and water conservation by building contour and terraces in their land as well as planting across the hills to reduce soil erosion.

- In the Eastern region, Soil testing should be done so that a proper deduction is made on soil composition and the crop that can grow best in their area.

- Key Planned activities for the next reporting period (quarter; maximum 1/2 page)

Please use the table below. Here kindly summarize key activities and related budget planned for the next quarter.

Quarter Work Plan

| Output | Activity | Target of activity | X | Person Responsible | Budget code |
| --- | --- | --- | --- | --- | --- |
|  |  |  | DEC | JAN | FEB | MAR | APR |  |  |
|  | Follow up on harvesting of beans | All farmer groups harvesting their beans | X | X |  |  |  | Resty, Kibirige, and Rogers |  |
| 1 | Branding of packaging materials | All groups Having their seed branded | X | XX |  |  |  | Farmers groups and field staff |  |
|  | Marketing search | All groups having their seed sold profitably | x | XX |  |  |  | Farmers groups |  |
|  | Farmers visit to NARO sites (foundation seed source) |  |  | XX |  |  |  | Resty and Rogers |  |
|  | Training in marketing |  |  |  | XX |  |  | Dr.Apollo |  |
|  | Seed sampling and testing |  |  | XX |  |  |  | Farmer groups |  |
|  | Business plan development |  |  |  | XX |  |  | Rogers and Dr. Apollo |  |
|  | Training in gender mainstreaming |  |  | XX |  |  |  | Dr.Apollo |  |
|  | Establishment demo site |  |  |  |  | XX |  | Resty , Rogers and |  |
|  | Exchange visits & field days |  |  |  |  |  | XX | Resty |  |
|  | Inspection & monitoring |  |  |  |  |  | XX | Resty and rogers |  |